## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Kế hoạch web elearning | 38 days? | May 6, 2024 8:00 AM | June 26, 2024 5:00 PM |  | 0
1 | Yes | Auto Scheduled | Landingpage | 12 days | May 6, 2024 8:00 AM | May 21, 2024 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Danh sách khóa học | 3.5 days | May 6, 2024 8:00 AM | May 9, 2024 12:00 PM |  | 2
3 | Yes | Auto Scheduled | Viết UI | 0.5 days | May 9, 2024 8:00 AM | May 9, 2024 12:00 PM |  | 3
4 | Yes | Auto Scheduled | Ghép api | 0.5 days | May 6, 2024 8:00 AM | May 6, 2024 12:00 PM |  | 3
5 | Yes | Auto Scheduled | Danh sách giảng viên | 0.5 days | May 15, 2024 8:00 AM | May 15, 2024 12:00 PM | 4 | 2
6 | Yes | Auto Scheduled | Viết UI | 0.5 days | May 15, 2024 8:00 AM | May 15, 2024 12:00 PM | 4 | 3
7 | Yes | Auto Scheduled | Ghép API | 0.5 days | May 15, 2024 8:00 AM | May 15, 2024 12:00 PM |  | 3
8 | Yes | Auto Scheduled | Thông tin liên hệ | 0.5 days | May 15, 2024 1:00 PM | May 15, 2024 5:00 PM | 7 | 2
9 | Yes | Auto Scheduled | Viết UI | 0.5 days | May 15, 2024 1:00 PM | May 15, 2024 5:00 PM | 4 | 3
10 | Yes | Auto Scheduled | Danh sách trải nghiệm khách hàng | 1.5 days | May 16, 2024 8:00 AM | May 17, 2024 12:00 PM | 9 | 2
11 | Yes | Auto Scheduled | Chi tiết trải nghiệm | 0.5 days | May 16, 2024 8:00 AM | May 16, 2024 12:00 PM | 8 | 3
12 | Yes | Auto Scheduled | Ghép API | 0.5 days | May 16, 2024 8:00 AM | May 16, 2024 12:00 PM |  | 4
13 | Yes | Auto Scheduled | Viết UI | 0.5 days | May 16, 2024 8:00 AM | May 16, 2024 12:00 PM |  | 4
14 | Yes | Auto Scheduled | Danh sách | 1 day | May 16, 2024 1:00 PM | May 17, 2024 12:00 PM |  | 3
15 | Yes | Auto Scheduled | Viết UI | 0.5 days | May 16, 2024 1:00 PM | May 16, 2024 5:00 PM | 13 | 4
16 | Yes | Auto Scheduled | Ghép API | 0.5 days | May 17, 2024 8:00 AM | May 17, 2024 12:00 PM | 15 | 4
17 | Yes | Auto Scheduled | Login/Signup | 1 day | May 21, 2024 8:00 AM | May 21, 2024 5:00 PM | 10 | 2
18 | Yes | Auto Scheduled | Viết UI | 4 hrs | May 21, 2024 8:00 AM | May 21, 2024 12:00 PM |  | 3
19 | Yes | Auto Scheduled | Ghép api | 1 day | May 21, 2024 8:00 AM | May 21, 2024 5:00 PM |  | 3
20 | Yes | Auto Scheduled | Chức năng chung | 17 days? | May 15, 2024 8:00 AM | June 6, 2024 5:00 PM | 17 | 1
21 | Yes | Auto Scheduled | Khóa học | 5 days? | May 22, 2024 8:00 AM | May 28, 2024 5:00 PM |  | 2
22 | Yes | Auto Scheduled | Danh sách khóa học | 1 day? | May 22, 2024 8:00 AM | May 22, 2024 5:00 PM | 17 | 3
23 | Yes | Auto Scheduled | Ghép api | 1 day? | May 22, 2024 8:00 AM | May 22, 2024 5:00 PM |  | 4
24 | Yes | Auto Scheduled | Viết UI | 1 day | May 22, 2024 8:00 AM | May 22, 2024 5:00 PM |  | 4
25 | Yes | Auto Scheduled | Chi tiết khóa học | 4 days? | May 23, 2024 8:00 AM | May 28, 2024 5:00 PM | 22 | 3
26 | Yes | Auto Scheduled | Danh sách bài học | 1 day? | May 23, 2024 8:00 AM | May 23, 2024 5:00 PM | 22 | 4
27 | Yes | Auto Scheduled | Viết UI | 1 day | May 23, 2024 8:00 AM | May 23, 2024 5:00 PM |  | 5
28 | Yes | Auto Scheduled | Ghép API | 1 day? | May 23, 2024 8:00 AM | May 23, 2024 5:00 PM |  | 5
29 | Yes | Auto Scheduled | Review | 1 day? | May 24, 2024 8:00 AM | May 24, 2024 5:00 PM | 26 | 4
30 | Yes | Auto Scheduled | Viết UI | 1 day? | May 24, 2024 8:00 AM | May 24, 2024 5:00 PM |  | 5
31 | Yes | Auto Scheduled | Ghép API | 1 day? | May 24, 2024 8:00 AM | May 24, 2024 5:00 PM |  | 5
32 | Yes | Auto Scheduled | Chi tiết bài học | 2 days? | May 27, 2024 8:00 AM | May 28, 2024 5:00 PM | 29 | 4
33 | Yes | Auto Scheduled | Viết UI | 1 day? | May 27, 2024 8:00 AM | May 27, 2024 5:00 PM |  | 5
34 | Yes | Auto Scheduled | Ghép api | 1 day? | May 27, 2024 8:00 AM | May 27, 2024 5:00 PM |  | 5
35 | Yes | Auto Scheduled | Review | 1 day? | May 28, 2024 8:00 AM | May 28, 2024 5:00 PM | 34 | 5
36 | Yes | Auto Scheduled | Viết UI | 1 day? | May 28, 2024 8:00 AM | May 28, 2024 5:00 PM |  | 6
37 | Yes | Auto Scheduled | Ghép API | 1 day? | May 28, 2024 8:00 AM | May 28, 2024 5:00 PM |  | 6
38 | Yes | Auto Scheduled | Bài test | 5 days? | May 29, 2024 8:00 AM | June 4, 2024 5:00 PM | 21 | 2
39 | Yes | Auto Scheduled | Danh sách bài test | 2 days | May 29, 2024 8:00 AM | May 30, 2024 5:00 PM | 21 | 3
40 | Yes | Auto Scheduled | Viết UI | 1 day | May 29, 2024 8:00 AM | May 29, 2024 5:00 PM |  | 4
41 | Yes | Auto Scheduled | Ghép api | 1 day | May 30, 2024 8:00 AM | May 30, 2024 5:00 PM | 40 | 4
42 | Yes | Auto Scheduled | Chi tiết bài test | 3 days? | May 31, 2024 8:00 AM | June 4, 2024 5:00 PM |  | 3
43 | Yes | Auto Scheduled | Quá trình test | 2 days | May 31, 2024 8:00 AM | June 3, 2024 5:00 PM | 39 | 4
44 | Yes | Auto Scheduled | Viết UI | 2 days | May 31, 2024 8:00 AM | June 3, 2024 5:00 PM |  | 5
45 | Yes | Auto Scheduled | Ghép api | 1 day | May 31, 2024 8:00 AM | May 31, 2024 5:00 PM |  | 5
46 | Yes | Auto Scheduled | Kết quả test | 1 day? | June 3, 2024 5:00 PM | June 4, 2024 5:00 PM | 43 | 4
47 | Yes | Auto Scheduled | Viết UI | 1 day? | June 4, 2024 8:00 AM | June 4, 2024 5:00 PM |  | 5
48 | Yes | Auto Scheduled | Ghép api | 0 days | June 3, 2024 5:00 PM | June 3, 2024 5:00 PM |  | 5
49 | Yes | Manually Scheduled | Thông tin người dùng | 1 day | May 29, 2024 8:00 AM | May 29, 2024 5:00 PM | 38 | 2
50 | Yes | Auto Scheduled | Viết UI | 1 day | May 15, 2024 8:00 AM | May 15, 2024 5:00 PM |  | 3
51 | Yes | Auto Scheduled | Ghép API | 0 days | May 16, 2024 8:00 AM | May 16, 2024 8:00 AM |  | 3
52 | Yes | Auto Scheduled | Thanh toán | 9 days? | May 21, 2024 8:00 AM | May 31, 2024 5:00 PM | 49 | 2
53 | Yes | Manually Scheduled | Generate mã QR code | 1 day? | May 30, 2024 8:00 AM | May 30, 2024 5:00 PM |  | 3
54 | Yes | Auto Scheduled | Viết UI | 1 day? | May 21, 2024 8:00 AM | May 21, 2024 5:00 PM |  | 4
55 | Yes | Auto Scheduled | Ghép api | 1 day | May 22, 2024 8:00 AM | May 22, 2024 5:00 PM |  | 4
56 | Yes | Auto Scheduled | Lịch sử thanh toán | 1 day? | May 31, 2024 8:00 AM | May 31, 2024 5:00 PM | 53 | 3
57 | Yes | Auto Scheduled | Viết UI | 1 day? | May 31, 2024 8:00 AM | May 31, 2024 5:00 PM |  | 4
58 | Yes | Auto Scheduled | Ghép api | 1 day | May 31, 2024 8:00 AM | May 31, 2024 5:00 PM |  | 4
59 | Yes | Auto Scheduled | Thông báo | 4 days? | June 3, 2024 8:00 AM | June 6, 2024 5:00 PM | 52 | 2
60 | Yes | Auto Scheduled | Danh sách thông báo | 2 days? | June 3, 2024 8:00 AM | June 4, 2024 5:00 PM |  | 3
61 | Yes | Auto Scheduled | Viết UI | 1 day? | June 3, 2024 8:00 AM | June 3, 2024 5:00 PM |  | 4
62 | Yes | Auto Scheduled | Ghép api | 2 days | June 3, 2024 8:00 AM | June 4, 2024 5:00 PM |  | 4
63 | Yes | Auto Scheduled | Chi tiết thông báo | 2 days? | June 5, 2024 8:00 AM | June 6, 2024 5:00 PM | 60 | 3
64 | Yes | Auto Scheduled | Viết UI | 1 day? | June 5, 2024 8:00 AM | June 5, 2024 5:00 PM |  | 4
65 | Yes | Auto Scheduled | Ghép api | 2 days | June 5, 2024 8:00 AM | June 6, 2024 5:00 PM |  | 4
66 | Yes | Auto Scheduled | Dành cho admin | 5 days? | June 6, 2024 5:00 PM | June 13, 2024 5:00 PM | 20 | 1
67 | Yes | Auto Scheduled | Học liệu | 1 day | June 6, 2024 5:00 PM | June 7, 2024 5:00 PM |  | 2
68 | Yes | Auto Scheduled | Chi tiết bài học(thêm, sửa xóa) | 1 day | June 6, 2024 5:00 PM | June 7, 2024 5:00 PM |  | 3
69 | Yes | Auto Scheduled | Viết UI | 0 days | June 6, 2024 5:00 PM | June 6, 2024 5:00 PM |  | 4
70 | Yes | Auto Scheduled | Ghép api | 1 day | June 7, 2024 8:00 AM | June 7, 2024 5:00 PM |  | 4
71 | Yes | Auto Scheduled | Danh sách khóa học | 0 days | June 6, 2024 5:00 PM | June 6, 2024 5:00 PM |  | 3
72 | Yes | Auto Scheduled | Viết UI | 0 days | June 6, 2024 5:00 PM | June 6, 2024 5:00 PM |  | 4
73 | Yes | Auto Scheduled | Ghép api | 0 days | June 6, 2024 5:00 PM | June 6, 2024 5:00 PM |  | 4
74 | Yes | Auto Scheduled | Chi tiết khóa học(thêm, sửa xóa) | 1 day | June 6, 2024 5:00 PM | June 7, 2024 5:00 PM | 71 | 3
75 | Yes | Auto Scheduled | Viết UI | 0 days | June 6, 2024 5:00 PM | June 6, 2024 5:00 PM |  | 4
76 | Yes | Auto Scheduled | Ghép api | 1 day | June 7, 2024 8:00 AM | June 7, 2024 5:00 PM |  | 4
77 | Yes | Auto Scheduled | Danh sách bài học | 0 days | June 7, 2024 5:00 PM | June 7, 2024 5:00 PM | 74 | 3
78 | Yes | Auto Scheduled | Viết UI | 0 days | June 7, 2024 5:00 PM | June 7, 2024 5:00 PM |  | 4
79 | Yes | Auto Scheduled | Ghép api | 0 days | June 7, 2024 5:00 PM | June 7, 2024 5:00 PM |  | 4
80 | Yes | Auto Scheduled | Quản lý người dùng | 4 days? | June 10, 2024 8:00 AM | June 13, 2024 5:00 PM | 67 | 2
81 | Yes | Auto Scheduled | Danh sách học viên | 1 day? | June 10, 2024 8:00 AM | June 10, 2024 5:00 PM | 67 | 3
82 | Yes | Auto Scheduled | Viết UI | 1 day? | June 10, 2024 8:00 AM | June 10, 2024 5:00 PM |  | 4
83 | Yes | Auto Scheduled | Ghép api | 1 day | June 10, 2024 8:00 AM | June 10, 2024 5:00 PM |  | 4
84 | Yes | Auto Scheduled | Chi tiết học viên(Thêm, sửa, xóa) | 1 day? | June 11, 2024 8:00 AM | June 11, 2024 5:00 PM | 81 | 3
85 | Yes | Auto Scheduled | Viết UI | 1 day? | June 11, 2024 8:00 AM | June 11, 2024 5:00 PM |  | 4
86 | Yes | Auto Scheduled | Ghép api | 1 day | June 11, 2024 8:00 AM | June 11, 2024 5:00 PM |  | 4
87 | Yes | Auto Scheduled | Danh sách giảng viên | 1 day? | June 12, 2024 8:00 AM | June 12, 2024 5:00 PM | 84 | 3
88 | Yes | Auto Scheduled | Viết UI | 1 day? | June 12, 2024 8:00 AM | June 12, 2024 5:00 PM |  | 4
89 | Yes | Auto Scheduled | Ghép api | 1 day | June 12, 2024 8:00 AM | June 12, 2024 5:00 PM |  | 4
90 | Yes | Auto Scheduled | Chi tiết giảng viên (thêm, sửa, xóa) | 1 day? | June 13, 2024 8:00 AM | June 13, 2024 5:00 PM | 87 | 3
91 | Yes | Auto Scheduled | Viết UI | 1 day? | June 13, 2024 8:00 AM | June 13, 2024 5:00 PM |  | 4
92 | Yes | Auto Scheduled | Ghép api | 1 day | June 13, 2024 8:00 AM | June 13, 2024 5:00 PM |  | 4
93 | Yes | Auto Scheduled | Dành cho Giảng viên | 2 days? | June 14, 2024 8:00 AM | June 17, 2024 5:00 PM | 66 | 1
94 | Yes | Auto Scheduled | Học liệu | 2 days? | June 14, 2024 8:00 AM | June 17, 2024 5:00 PM |  | 2
95 | Yes | Auto Scheduled | Chi tiết bài học (Thêm, sửa) | 1 day? | June 14, 2024 8:00 AM | June 14, 2024 5:00 PM |  | 3
96 | Yes | Auto Scheduled | Viết UI | 1 day? | June 14, 2024 8:00 AM | June 14, 2024 5:00 PM |  | 4
97 | Yes | Auto Scheduled | Ghép api | 1 day | June 14, 2024 8:00 AM | June 14, 2024 5:00 PM |  | 4
98 | Yes | Auto Scheduled | Danh sách khóa học | 1 day? | June 14, 2024 8:00 AM | June 14, 2024 5:00 PM |  | 3
99 | Yes | Auto Scheduled | Viết UI | 1 day? | June 14, 2024 8:00 AM | June 14, 2024 5:00 PM |  | 4
100 | Yes | Auto Scheduled | Ghép api | 1 day | June 14, 2024 8:00 AM | June 14, 2024 5:00 PM |  | 4
101 | Yes | Auto Scheduled | Chi tiết khóa học(thêm, sửa) | 1 day? | June 14, 2024 8:00 AM | June 14, 2024 5:00 PM |  | 3
102 | Yes | Auto Scheduled | Viết UI | 1 day? | June 14, 2024 8:00 AM | June 14, 2024 5:00 PM |  | 4
103 | Yes | Auto Scheduled | Ghép api | 1 day | June 14, 2024 8:00 AM | June 14, 2024 5:00 PM |  | 4
104 | Yes | Auto Scheduled | Danh sách bài học | 2 days? | June 14, 2024 8:00 AM | June 17, 2024 5:00 PM |  | 3
105 | Yes | Auto Scheduled | Viết UI | 1 day? | June 14, 2024 8:00 AM | June 14, 2024 5:00 PM |  | 4
106 | Yes | Auto Scheduled | Ghép api | 2 days | June 14, 2024 8:00 AM | June 17, 2024 5:00 PM |  | 4
107 | Yes | Auto Scheduled | Danh cho học viên | 2 days | June 18, 2024 8:00 AM | June 19, 2024 5:00 PM | 93 | 1
108 | Yes | Auto Scheduled | Danh sách khóa học | 2 days | June 18, 2024 8:00 AM | June 19, 2024 5:00 PM |  | 2
109 | Yes | Auto Scheduled | Viết UI | 2 days | June 18, 2024 8:00 AM | June 19, 2024 5:00 PM |  | 3
110 | Yes | Auto Scheduled | Ghép api | 1 day | June 18, 2024 8:00 AM | June 18, 2024 5:00 PM |  | 3
111 | Yes | Auto Scheduled | Chi tiết khóa học | 2 days | June 18, 2024 8:00 AM | June 19, 2024 5:00 PM |  | 2
112 | Yes | Auto Scheduled | Viết UI | 2 days | June 18, 2024 8:00 AM | June 19, 2024 5:00 PM |  | 3
113 | Yes | Auto Scheduled | Ghép api | 1 day | June 18, 2024 8:00 AM | June 18, 2024 5:00 PM |  | 3
114 | Yes | Auto Scheduled | Viết tài liệu | 5 days | June 20, 2024 8:00 AM | June 26, 2024 5:00 PM | 107 | 1
115 | Yes | Auto Scheduled | Tài liệu hướng dẫn sử dụng | 4 days | June 20, 2024 8:00 AM | June 25, 2024 5:00 PM |  | 2
116 | Yes | Auto Scheduled | Tài liệu thiết kế hế thống | 1 day | June 26, 2024 8:00 AM | June 26, 2024 5:00 PM | 115 | 2
117 | Yes | Auto Scheduled | Deploy web | 5 days | May 6, 2024 8:00 AM | May 10, 2024 5:00 PM |  | 1
118 | Yes | Auto Scheduled | Đẩy IOS | 5 days | May 6, 2024 8:00 AM | May 10, 2024 5:00 PM |  | 2
119 | Yes | Auto Scheduled | Đẩy android | 5 days | May 6, 2024 8:00 AM | May 10, 2024 5:00 PM |  | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Management | M | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Project Manager | P | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Analyst | A | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Developer | D | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Testers | T | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Trainers | T | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Technical Communicators | T | Work |  |  |  |  | 100% | $0.00/h | 0
8 | Deployment Team | D | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Landingpage | Developer | 0 | 96h | 100%
Danh sách khóa học | Developer | 0 | 28h | 100%
Danh sách giảng viên | Developer | 0 | 4h | 100%
Thông tin liên hệ | Developer | 0 | 4h | 100%
Danh sách trải nghiệm khách hàng | Developer | 0 | 12h | 100%
Login/Signup | Developer | 0 | 8h | 100%
Chức năng chung | Developer | 0 | 136h | 100%
Khóa học | Developer | 0 | 40h | 100%
Bài test | Developer | 0 | 40h | 100%
Danh sách bài test | Developer | 0 | 16h | 100%
Chi tiết bài test | Developer | 0 | 24h | 100%
Quá trình test | Developer | 0 | 16h | 100%
Kết quả test | Developer | 0 | 8h | 100%
Thông tin người dùng | Developer | 0 | 8h | 100%
Thanh toán | Developer | 0 | 72h | 100%
Generate mã QR code | Developer | 0 | 8h | 100%
Lịch sử thanh toán | Developer | 0 | 8h | 100%
Thông báo | Developer | 0 | 32h | 100%
Danh sách thông báo | Developer | 0 | 16h | 100%
Chi tiết thông báo | Developer | 0 | 16h | 100%
Dành cho admin | Developer | 0 | 40h | 100%
Ghép api | Developer | 0 | 8h | 100%
Ghép api | Developer | 0 | 0h | 100%
Ghép api | Developer | 0 | 8h | 100%
Ghép api | Developer | 0 | 0h | 100%
Ghép api | Developer | 0 | 8h | 100%
Ghép api | Developer | 0 | 8h | 100%
Ghép api | Developer | 0 | 8h | 100%
Ghép api | Developer | 0 | 8h | 100%
Dành cho Giảng viên | Developer | 0 | 16h | 100%
Ghép api | Developer | 0 | 8h | 100%
Ghép api | Developer | 0 | 8h | 100%
Ghép api | Developer | 0 | 8h | 100%
Ghép api | Developer | 0 | 16h | 100%
Danh cho học viên | Developer | 0 | 16h | 100%
Viết UI | Developer | 0 | 16h | 100%
Chi tiết khóa học | Developer | 0 | 16h | 100%
Viết tài liệu | Developer | 0 | 40h | 100%
Tài liệu hướng dẫn sử dụng | Developer | 0 | 32h | 100%
Tài liệu thiết kế hế thống | Developer | 0 | 8h | 100%
Deploy web | Developer | 0 | 40h | 100%
Đẩy IOS | Developer | 0 | 40h | 100%
Đẩy android | Project Manager | 0 | 40h | 100%